## Projected
|  | 1st July | 8th July | 15th July | 22nd July | 29th July | 5th Aug | 12th Aug | 19th Aug | 26th Aug | 2nd Sept | 9th Sept | 16th Sept | 23rd Sept | 30th Sept | 7th Oct | 14th Oct | 21st Oct | 28th Oct | 4th Nov | 11th Nov | 18th Nov | 25th Nov | 2nd Dec | 9th Dec | 16th Dec | 23rd Dec | 30th Dec | 6th Jan | 13th Jan | 20th Jan | 27th Jan | 3rd Feb | 10th Feb | 17th Feb | 24th Feb | 3rd Mar | 10th Mar | 17th Mar | 24th Mar | 31st Mar | 7th April | 14th April | 21st April | 28th Aptil | 5th May | 12th May | 19th May | 26th May | 2nd June
WP | Task |  | Wk1 | Wk2 | Wk3 | WK4 | WK5 | WK6 | Easter | WK7 | WK8 | WK9 | WK10 | WK11 | WK12 | WK13 | WK14 | WK15 | WK16 | WK17 | WK18 | WK19 | WK20 | WK21 | WK22 | WK23 | WK24 | WK25 | WK26 | WK27 | WK28 | WK29 | WK30 | WK31 | WK32 | WK33 | WK34 | WK35 | WK36 | WK37 | WK38 | WK39 | WK40 | WK41 | WK42 | WK43 | WK44 | WK45 | WK46 | WK47
SOI
Finalise SOI
Discussions with mentor
Literature Review
Research | bar: WK7 to WK21
Data gathering of related studies | bar: WK10 to WK21
Introduction and Dangers of fake news | bar: WK12 to WK15
Mitigation Techniques | bar: WK15 to WK18
Classifiers and Feature Extractors | bar: WK18 to WK21
Conclusion | bar: WK21
Research Methodology
Research and Data Gathering | bar: WK7 to WK33
Finding a good dataset | bar: WK19 to WK25
Hypothesis and Research Questions | bar: WK19 to WK20
Discussion of Research Methods | bar: WK26
Research Pipeline | bar: WK33
Prototype Implementation | bar: WK27 to WK32
Model Construction and Evaluation | bar: WK31 to WK32
Prototype
Data loading and probing | bar: WK25 to WK27
Data Cleaning | bar: WK27
Preprocessing of data | bar: WK28
Data splitting | bar: WK29
Construction of Classifiers | bar: WK29 to WK31
Finding the ideal hyperparameters | bar: WK31
Data training and testing | bar: WK31 to WK32
Tweaking of prototype | bar: WK30 to WK32
Data Collection & Analysis
Prototype Execution | bar: WK31 to WK33
Analysis of metrics | bar: WK33 to WK34
Aggregate metrics | bar: WK34 to WK35
Discussion of Results
Write prototype evaluation | bar: WK35
Write dataset evaluation | bar: WK34 to WK35
Write hypothesis testing | bar: WK36
Calculate average results | bar: WK35
Compare results with each classifier | bar: WK37
Other sections (Conclusion, Introduction, Abstract)
Finalise conclusion & recommendations | bar: WK37 to WK38
Finalise Introduction | bar: WK39 to WK40
Finalise Abstract | bar: WK41
Review and perfect the all above sections | bar: WK37 to WK47

## Actual
|  | 1st July | 8th July | 15th July | 22nd July | 29th July | 5th Aug | 12th Aug | 19th Aug | 26th Aug | 2nd Sept | 9th Sept | 16th Sept | 23rd Sept | 30th Sept | 7th Oct | 14th Oct | 21st Oct | 28th Oct | 4th Nov | 11th Nov | 18th Nov | 25th Nov | 2nd Dec | 9th Dec | 16th Dec | 23rd Dec | 30th Dec | 6th Jan | 13th Jan | 20th Jan | 27th Jan | 3rd Feb | 10th Feb | 17th Feb | 24th Feb | 3rd Mar | 10th Mar | 17th Mar | 24th Mar | 31st Mar | 7th April | 14th April | 21st April | 28th Aptil | 5th May | 12th May | 19th May | 26th May | 2nd June
WP | Task |  | Wk1 | Wk2 | Wk3 | WK4 | WK5 | WK6 | Easter | WK7 | WK8 | WK9 | WK10 | WK11 | WK12 | WK13 | WK14 | WK15 | WK16 | WK17 | WK18 | WK19 | WK20 | WK21 | WK22 | WK23 | WK24 | WK25 | WK26 | WK27 | WK28 | WK29 | WK30 | WK31 | WK32 | WK33 | WK34 | WK35 | WK36 | WK37 | WK38 | WK39 | WK40 | WK41 | WK42 | WK43 | WK44 | WK45 | WK46 | WK47
SOI
Finalise SOI
Discussions with mentor
Literature Review
Research | bar: WK7 to WK25
Data gathering of related studies | bar: WK10 to WK25
Introduction and Dangers of fake news | bar: WK12 to WK15
Mitigation Techniques | bar: WK15 to WK18
Classifiers and Feature Extractors | bar: WK18 to WK25
Conclusion | bar: WK25
Research Methodology
Research and Data Gathering | bar: WK7 to WK25; WK30 to WK35
Finding a good dataset | bar: WK24 to WK25; WK30
Hypothesis and Research Questions | bar: WK30 to WK31
Discussion of Research Methods | bar: WK30
Research Pipeline
Prototype Implementation | bar: WK34 to WK35
Model Construction and Evaluation
Prototype
Data Loading and probing | bar: WK30 to WK33
Data Cleaning | bar: WK33 to WK35
Preprocessing of data
Data splitting
Construction of Classifiers
Finding the ideal hyperparameters
Data training and testing
Tweaking of prototype
Data Collection & Analysis
Prototype Execution
Analysis of metrics
Aggregate metrics
Discussion of Results
Write prototype evaluation
Write dataset evaluation
Write hypothesis testing
Calculate average results
Compare results with each classifier
Other sections (Conclusion, Introduction, Abstract)
Finalise conclusion & recommendations
Finalise Introduction
Finalise Abstract
Review and perfect the all above sections