## Projected
|  | 1st July | 8th July | 15th July | 22nd July | 29th July | 5th Aug | 12th Aug | 19th Aug | 26th Aug | 2nd Sept | 9th Sept | 16th Sept | 23rd Sept | 30th Sept | 7th Oct | 14th Oct | 21st Oct | 28th Oct | 4th Nov | 11th Nov | 18th Nov | 25th Nov | 2nd Dec | 9th Dec | 16th Dec | 23rd Dec | 30th Dec | 6th Jan | 13th Jan | 20th Jan | 27th Jan | 3rd Feb | 10th Feb | 17th Feb | 24th Feb | 3rd Mar | 10th Mar | 17th Mar | 24th Mar | 31st Mar | 7th April | 14th April | 21st April | 28th Aptil | 5th May | 12th May | 19th May | 26th May | 2nd June
WP | Task |  | Wk1 | Wk2 | Wk3 | WK4 | WK5 | WK6 | Easter | WK7 | WK8 | WK9 | WK10 | WK11 | WK12 | WK13 | WK14 | WK15 | WK16 | WK17 | WK18 | WK19 | WK20 | WK21 | WK22 | WK23 | WK24 | WK25 | WK26 | WK27 | WK28 | WK29 | WK30 | WK31 | WK32 | WK33 | WK34 | WK35 | WK36 | WK37 | WK38 | WK39 | WK40 | WK41 | WK42 | WK43 | WK44 | WK45 | WK46 | WK47
SOI
Finalise SOI
Discussions with mentor
Literature Review
Research | bar: WK7 to WK21
Data gathering of related studies | bar: WK10 to WK21
Introduction and Dangers of fake news | bar: WK12 to WK15
Mitigation Techniques | bar: WK15 to WK18
Classifiers and Feature Extractors | bar: WK18 to WK21
Conclusion | bar: WK21
Research Methodology
Research and Data Gathering | bar: WK7 to WK33
Finding a good dataset | bar: WK19 to WK25
Hypothesis and Research Questions | bar: WK19 to WK20
Discussion of Research Methods | bar: WK26
Research Pipeline | bar: WK33
Prototype Implementation | bar: WK27 to WK32
Model Construction and Evaluation | bar: WK31 to WK32
Prototype
Data loading and probing | bar: WK25 to WK27
Data Cleaning | bar: WK27
Preprocessing of data | bar: WK28
Data splitting | bar: WK29
Construction of Classifiers | bar: WK29 to WK31
Finding the ideal hyperparameters | bar: WK31
Data training and testing | bar: WK31 to WK32
Tweaking of prototype | bar: WK30 to WK32
Data Collection & Analysis
Prototype Execution | bar: WK31 to WK33
Analysis of metrics | bar: WK33 to WK34
Aggregate metrics | bar: WK34 to WK35
Discussion of Results
Write prototype evaluation | bar: WK35
Write dataset evaluation | bar: WK34 to WK35
Write hypothesis testing | bar: WK36
Calculate average results | bar: WK35
Compare results with each classifier | bar: WK37
Other sections (Conclusion, Introduction, Abstract)
Finalise conclusion & recommendations | bar: WK37 to WK38
Finalise Introduction | bar: WK39 to WK40
Finalise Abstract | bar: WK41
Review and perfect the all above sections | bar: WK37 to WK47

## Actual
|  | 1st July | 8th July | 15th July | 22nd July | 29th July | 5th Aug | 12th Aug | 19th Aug | 26th Aug | 2nd Sept | 9th Sept | 16th Sept | 23rd Sept | 30th Sept | 7th Oct | 14th Oct | 21st Oct | 28th Oct | 4th Nov | 11th Nov | 18th Nov | 25th Nov | 2nd Dec | 9th Dec | 16th Dec | 23rd Dec | 30th Dec | 6th Jan | 13th Jan | 20th Jan | 27th Jan | 3rd Feb | 10th Feb | 17th Feb | 24th Feb | 3rd Mar | 10th Mar | 17th Mar | 24th Mar | 31st Mar | 7th April | 14th April | 21st April | 28th Aptil | 5th May | 12th May | 19th May | 26th May | 2nd June
WP | Task |  | Wk1 | Wk2 | Wk3 | WK4 | WK5 | WK6 | Easter | WK7 | WK8 | WK9 | WK10 | WK11 | WK12 | WK13 | WK14 | WK15 | WK16 | WK17 | WK18 | WK19 | WK20 | WK21 | WK22 | WK23 | WK24 | WK25 | WK26 | WK27 | WK28 | WK29 | WK30 | WK31 | WK32 | WK33 | WK34 | WK35 | WK36 | WK37 | WK38 | WK39 | WK40 | WK41 | WK42 | WK43 | WK44 | WK45 | WK46 | WK47
SOI
Finalise SOI
Discussions with mentor
Literature Review
Research | bar: WK7 to WK25
Data gathering of related studies | bar: WK10 to WK25
Introduction and Dangers of fake news | bar: WK12 to WK15
Mitigation Techniques | bar: WK15 to WK18
Classifiers and Feature Extractors | bar: WK18 to WK25
Conclusion | bar: WK25
Research Methodology
Research and Data Gathering | bar: WK7 to WK25; WK30 to WK35
Finding a good dataset | bar: WK24 to WK25; WK30
Hypothesis and Research Questions | bar: WK30 to WK31
Discussion of Research Methods | bar: WK30
Research Pipeline | bar: WK38
Prototype Implementation | bar: WK31 to WK38
Model Construction and Evaluation | bar: WK37 to WK38
Prototype
Data Loading and probing | bar: WK30 to WK33
Data Cleaning | bar: WK33 to WK34
Preprocessing of data | bar: WK35 to WK36
Data splitting | bar: WK37
Construction of Classifiers | bar: WK37 to WK39
Finding the ideal hyperparameters | bar: WK39
Data training and testing | bar: WK39 to WK40
Tweaking of prototype | bar: WK38 to WK40
Data Collection & Analysis
Prototype Execution | bar: WK39 to WK41
Analysis of metrics | bar: WK41 to WK42
Aggregate metrics | bar: WK42 to WK43
Discussion of Results
Write prototype evaluation | bar: WK44
Write dataset evaluation | bar: WK43 to WK44
Write hypothesis testing | bar: WK45
Calculate average results | bar: WK44
Compare results with each classifier | bar: WK46
Other sections (Conclusion, Introduction, Abstract)
Finalise conclusion & recommendations | bar: WK43 to WK44
Finalise Introduction | bar: WK45 to WK46
Finalise Abstract | bar: WK47
Review and perfect the all above sections | bar: WK43 to WK47